## Slide 1: JOCKEY CLUB OF NORTH PORT POA INC BYLAW REVIEW
David Casarsa
Vice President

## Slide 2: AIM
To establish a committee and conditions to review, update, approve and disseminate the Bylaws and Declaration of Covenants and Restrictions of the Jockey Club.
ENDSTATE. A Committee, approved by the membership, to review and update our documents and disseminate same for approval by the membership at the Annual General Meeting in March 2018.

## Slide 3: SCOPE
HOA governing documents consist of three components:
  Articles of Incorporation – legal framework for the HOA;
  Bylaws – rules and regulations for the Board of Directors;
  Declaration of Covenants and Restrictions – rules and regulations affecting the members of the HOA
Focus of review will be on Bylaws and Declaration of Covenants and Restrictions.
Article of Incorporation to remain extant
  Last major review conducted in 1996 with the transfer of Schedule B – “Homesite Lots” to a developer. Now known as Charleston Park.

## Slide 4: BACKGROUND
Focus upon work done in 2013 on Bylaws and Declarations of Covenants and Restrictions.
Documents were prepared by a committee, submitted to owners with a write in ballot and approved at the Annual Meeting in 2013.
Subsequent legal review raised numerous comments and additions requiring a subsequent review and vote by members.
Issue died.
Current 2006 documents were approved in that year but not implemented until 2015.

## Slide 5: OUTLINE
Review 2013 draft documents making any additions/updates as desired by the membership and required by law.
Jockey Club review to consist of identification of problem areas, new requirements and drafting same in “bullet form”
Submission of draft documents for legal review and preparation of additions/amendments.
Transmission of draft documents to membership for vote, write in ballot plus voting at Annual General Meeting in March 2018.
Vote will be “all or nothing”. Simple, less time consuming, less costly.
  Members had voted in favour of all regulations in a section by section vote in 2013.

## Slide 6: TIMELINES
Feb 17 - 2013 draft given cursory review by lawyer for content and cost estimate.
Mar 17 – Formation of Bylaw Committee
Apr-Sep 17 – Monthly committee meetings seeking member input
  Members encouraged to attend meetings to provide input.
  Member comments to be provided in writing or email.
Oct 17 – Send to lawyer for legal review.
Nov/Dec 17 – Final adjustments to draft.
Jan 18 – Promulgation to membership for review and vote by mail, fax, email.
Mar 18 – Final approval at Annual General Meeting.
Apr/May 18 – Recording of documents with Sarasota County and dissemination to membership.

## Slide 7: KEY ISSUES - BYLAWS
Change Annual Meeting date from second Tuesday to second Wednesday in March. Alternate date is Thursday.
  Eliminates conflicts with Municipal, State and Federal elections.
Add bylaw on electronic voting.
Statement on Reserves and authorities.

## Slide 8: KEY ISSUES – DECLARATION OF COVENANTS/RESTRICTIONS
Special Assessments – Board or Membership? Limits of auth?
Home standards – in 1996 docs, but not included in 1998/2006.
  Covered by ECC Rules - 2007
Owner/Renter screening
  No LLC or Trust Co equivalents
  No denials based on criminal records
Pets/animals – numbers and noise
Fences
Vehicles
Grass
Energy Conservation

## Slide 9: WAY AHEAD
15 Mar 17 - Authorization of Bylaw Committee (3-5 pers)
  Required skill sets:
    Proficient in MS Word, MS Power Point, Skype and email
    Good reading, writing and verbal communications
    Personal interaction with officials in discussing bylaws
End Mar 17 – Draft Bylaws/Covenants posted on website.
  Hard copies printed at Clubhouse for $5.00
Apr 17 – First Committee Meeting – Date TBA
  Monthly Meetings; e-mail address for queries/comments
  Open to membership for input/discussion
Fall 17 – Draft presented for legal review
Jan 18 – Distribution to membership
Mar 18 – AGM – Approval
Apr 18 – Recording with Sarasota County

## Slide 10: MOTION
To establish a Bylaw Review Committee to review and update Jockey Club Bylaws and Declaration of Covenants and Restrictions based on the 2013 draft with a view to approving new regulations at the AGM in March 2018.
The Committee shall consist of those members identified at the Jockey Club AGM held on 15 March 2017. The Committee has the right to add additional members subject to Board concurrence.

## Slide 11: CONTACTS (as at 20 March 2017)
Website: Documentation and updates
Jockeyclubnorthport.com DOCUMENTS/BYLAW REVIEW
In Person: Attend monthly committee meetings
By Mail: Jockey Club of North Port POA Inc
3050 Pan American Blvd
North Port, Fl, 34287
Attn: Bylaw Committee
E Mail: jockeyclubnorthport@gmail.com
“Bylaw Review” in subject line